iOS ADE Enrolment Policy Migration

Diagnosis, test plan and controlled implementation plan

| Scope | iOS/iPadOS Automated Device Enrolment (ADE) |
| --- | --- |
| Purpose | Validate and migrate legacy Profiles to new Policies |
| Version | 1.0 ¦ 9 July 2026 |

KEY FINDING Changing the default enrolment Policy does not migrate serial numbers that remain assigned to a legacy Profile. Explicitly reassign test and production serials to the new Policy before wiping or activating them.

# 1. Diagnosis and immediate remediation

The observed behaviour is consistent with a device serial number that remains assigned to a legacy Automated Device Enrolment (ADE) Profile. New iOS/iPadOS ADE Policies coexist with legacy Profiles, and existing Profile assignments are not moved automatically. The default Policy is selected per ADE token; it is not a tenant-wide replacement rule.

Policy selection at activation Apple device serial -> Apple Business Manager / Apple School Manager MDM server -> Intune ADE token Explicit serial assignment -> the assigned legacy Profile or new Policy is used. No explicit serial assignment -> the default Policy for that ADE token is used.

## Immediate remediation steps

Open the ADE token that owns the test device: Devices > Enrolment > Apple > Enrolment program tokens > [token] > Devices.

Search for the device serial number and confirm it is assigned to the expected Apple Business Manager or Apple School Manager MDM server and Intune ADE token.

From Enrolment policies > [new Policy] > Devices, select the exact serial number and choose Assign policy.

Confirm the new Policy lists the serial and the legacy Profile no longer lists it. Sync the token and wait for the assignment to be visible in Intune.

Factory-reset only after the server-side policy assignment is confirmed, then activate the device on a reliable network.

Do not release the device from Apple Business Manager or Apple School Manager merely to change enrolment Policy. The required action is the serial-number policy reassignment in Intune.

# 2. Test plan

Use dedicated test devices and complete each test against the same ADE token and device persona that will be used in production. Keep the legacy Profile available until rollback has been demonstrated.

| Test | Action | Pass criterion |
| --- | --- | --- |
| 1. Baseline | Capture the test serial, ABM/ASM MDM server, ADE token, legacy Profile, authentication method and key settings. | The current assignment is visible and documented. |
| 2. Direct migration | Assign the exact serial to the new Policy from the Policy Devices tab, then sync the token. | The new Policy lists the serial; the legacy Profile does not. |
| 3. Re-enrolment | Factory-reset only after the server-side assignment is visible. Activate on a reliable, non-captive network. | The expected Setup Assistant journey and Policy settings apply. |
| 4. Identity and compliance | Complete the intended identity flow, then validate registration, compliance and access to a Conditional Access-protected resource. | Correct user affinity, Entra registration and compliant status. |
| 5. Workload parity | Test Wi-Fi, certificates, VPN, restrictions, required apps, device naming and support contact details. | All required configuration arrives and works. |
| 6. Rollback | Reassign the same test serial to the legacy Profile and wipe again. | The previous enrolment experience returns successfully. |
| 7. Default validation | Use a separate, previously unassigned test serial after setting the new default on a safe test token or during planned cutover. | The device receives the new default Policy. |

Test evidence to retain: serial number, token name, policy/profile assignment screenshots, activation timestamp and time zone, device model, iOS/iPadOS version, compliance result, and any Company Portal or Microsoft Authenticator diagnostics.

# 3. Migration readiness

Create the new Policies in parallel with the existing Profiles. Match existing configuration deliberately, then record intentional changes before any production serial assignment is moved.

| Area | Required decision and validation |
| --- | --- |
| Company Portal | New Policies do not automatically deploy Company Portal. Choose JIT registration or deploy Company Portal explicitly as a required, device-licensed VPP app. |
| Authentication | Use Setup Assistant with modern authentication for user-affinity devices. Validate multi-factor authentication and the first work-app sign-in. |
| Policy targeting | Update dynamic groups and assignment filters that reference enrollmentProfileName so the new Policy names are included. |
| Await final configuration | Set to Yes unless a tested exception is required. Confirm critical configuration arrives before the home screen is released. |
| Naming and shared scenarios | Carry over the device name template, locked enrolment, user affinity, shared mode and Shared iPad settings. Use separate Policies for genuinely different personas. |

IMPORTANT If Setup Assistant with modern authentication and JIT registration are used, deploy the Microsoft Entra SSO extension and Microsoft Authenticator, then test the first sign-in to the nominated work app. If Company Portal remains part of the design, deploy it separately and validate its app configuration.

## Readiness checklist

Inventory every ADE token, legacy Profile, assigned serial range, device persona, default configuration and dependent group or filter.

Create one new Policy for each distinct enrolment persona; avoid using a global default to collapse genuine differences.

Confirm Apple MDM Push and VPP tokens are valid and that Company Portal licensing and app assignment are correct where relevant.

Update targeting that uses enrollmentProfileName, including dynamic groups, filters, app assignments and configuration policy assignments.

Set Await final configuration to Yes unless there is a documented and tested exception.

Prepare end-user communications and support procedures for device wipes, enrolment changes and Conditional Access remediation.

# 4. Controlled implementation plan

Phase 1 - Build and review: Create new Policies, map their settings to the legacy Profile inventory, and approve all configuration deltas.

Phase 2 - Technical pilot: Explicitly migrate IT-owned test serials, complete the test plan, and retain a proven rollback path to the legacy Profile.

Phase 3 - Persona pilot: Move a small representative group for each user-affinity, userless, shared-device and Shared iPad scenario in use. Monitor enrolment, compliance and app delivery.

Phase 4 - Batch migration: Reassign production serials to the appropriate new Policy in controlled batches. Maintain an exception list and pause further batches if pass criteria are not met.

Phase 5 - Default cutover: After pilot success, set the new Policy as the default on each relevant ADE token so new or unassigned inventory receives the correct Policy.

Phase 6 - Retirement: Retain legacy Profiles through the agreed rollback period. Retire them only after no active serials, naming dependencies, filters or support processes rely on them.

## Rollout controls and rollback

Do not use the default Policy as the migration mechanism for serials already assigned to a legacy Profile; explicitly reassign them.

Existing enrolled devices can remain in service. Enrolment Policy changes take effect when devices are factory-reset and activated again.

For a failed batch, stop subsequent migrations, restore the affected serial assignment to the legacy Profile, and wipe only the affected test or recovery devices.

Do not delete legacy Profiles during testing. Confirm device naming remains enforced by the replacement Policy before retirement.

## Success criteria

Every migrated serial is assigned to the intended new Policy and no unapproved serial remains on a legacy Profile.

Setup Assistant, user affinity, Entra registration, compliance and Conditional Access work for each supported persona.

Required applications, certificates, Wi-Fi, VPN, restrictions and device naming arrive within the agreed provisioning window.

No critical enrolment, compliance or access incidents occur during the defined monitoring period for a rollout wave.

A documented rollback test has passed before production cutover.

# References

1. Microsoft Intune Customer Success - New iOS/iPadOS, visionOS, tvOS and macOS ADE enrollment policies experience - https://techcommunity.microsoft.com/blog/intunecustomersuccess/new-iosipados-visionos-tvos-and-macos-ade-enrollment-policies-experience/4393531

2. Microsoft Learn - Tutorial: Set up Microsoft Intune enrollment for iOS/iPadOS devices in Apple Business - https://learn.microsoft.com/en-us/intune/device-enrollment/apple/tutorial-automated-ios

3. Microsoft Learn - Set up automated device enrollment (ADE) for iOS/iPadOS - https://learn.microsoft.com/en-us/intune/device-enrollment/apple/setup-automated-ios

4. Microsoft Learn - Set up just-in-time registration in Microsoft Intune - https://learn.microsoft.com/en-us/intune/device-enrollment/apple/setup-just-in-time-registration

5. Microsoft Learn - Assignment filter properties and operators reference - https://learn.microsoft.com/en-us/intune/fundamentals/filters/ref-device-properties